# NZERU TUTORING PLATFORM DEVELOPMENT TIMELINE

## Online Tutoring Platform - Executive Summary

February - June 2026
17-Week Development Sprint
February 04, 2026

# Project Overview

| Item | Details |
| --- | --- |
| Project | Online Tutoring Platform for Malawi |
| Timeline | February 3 - May 31, 2026 (17 weeks) |
| Launch Date | June 1, 2026 |
| Team Size | 4-5 developers + QA + PM |
| Budget |  |

This document provides a high-level overview of the development timeline and key milestones for launching the online tutoring platform by June 2026.

# Development Phases

| Phase | Weeks | Dates | Focus Areas | Key Deliverables |
| --- | --- | --- | --- | --- |
| 1. Foundation | 1-2 | Feb 3-16 | Setup, infrastructure, authentication | Dev environment, database, login system |
| 2. Core Features | 3-8 | Feb 17 - Mar 30 | Search, booking, profiles, scheduling | Tutor discovery, booking system, dashboards |
| 3. Virtual Classroom | 9-11 | Mar 31 - Apr 20 | Video, whiteboard, chat | Live classroom with video and interactive tools |
| 4. Payments | 12-13 | Apr 21 - May 4 | Payment gateway, DPO, escrow, payouts | Payment processing and tutor earnings |
| 5. Verification | 14 | May 5-11 | Session tracking, completion | Attendance tracking and verification |
| 6. Testing | 15-16 | May 12-25 | QA, bug fixes, optimization | Tested, optimized platform |
| 7. Launch Prep | 17 | May 26-31 | Deployment, documentation | Live platform ready for users |

# Key Milestones

February 16, 2026 - Foundation Complete

Development environment operational

User authentication working

Database schema implemented

March 2, 2026 - Search & Discovery Ready

Tutor search and filtering functional

Tutor profiles live

Search UI complete

March 30, 2026 - Booking System Live

Scheduling and calendar working

Booking flow complete

Email notifications active

Student and tutor dashboards ready

April 20, 2026 - Virtual Classroom Complete

Video communication working

Interactive whiteboard functional

Chat and session controls ready

May 4, 2026 - Payment System Operational

Payment processing integrated

Escrow system working

Tutor payouts configured

May 11, 2026 - Session Management Ready

Attendance tracking active

Completion verification working

Payment release automated

May 25, 2026 - Testing Complete

All bugs fixed

Performance optimized

Security verified

May 31, 2026 - Production Deployed

Platform live

Monitoring active

Documentation complete

June 2026 - PUBLIC LAUNCH

Platform accessible to all users

Marketing campaign begins

# Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js + React | User interface, responsive design |
| Backend | Node.js + Firestore | API services, business logic |
| Database | PostgreSQL | Data storage |
| Caching | Redis | Performance optimization |
| Video | Agora.io | Virtual classroom, video calls |
| Storage | Cloudflare R2 / AWS S3 | File storage, recordings |
| Hosting | Vercel + Render | Cloud deployment |
| Payments | TBD | Payment processing |

# Team Structure

| Role | Count | Key Responsibilities |
| --- | --- | --- |
| Full-stack Developers | 2 | Backend API, frontend UI, database |
| Frontend Developer | 1 | UI/UX, responsive design |
| QA Engineer | 1 | Testing, quality assurance |
| DevOps Engineer | 0.5 | Infrastructure, deployment (part-time) |
| Project Manager | 0.5 | Timeline, coordination (part-time) |

# MVP Features Checklist

## Phase 1 Features (Launch - June 2026)

✓ User registration and authentication (students & tutors)

✓ User profiles with role-based access

✓ Tutor search with filters (subject, price, rating, availability)

✓ Booking and scheduling system

✓ Calendar integration

✓ Email notifications (reminders, confirmations)

✓ Virtual classroom with video and audio

✓ Interactive whiteboard

✓ In-session chat

✓ Payment processing and escrow

✓ Tutor payout system

✓ Session verification and completion

✓ Attendance tracking

✓ Ratings and reviews

✓ Student and tutor dashboards

✓ Material sharing

## Phase 2 Features (Post-Launch - July-Aug 2026)

Group lessons (multiple students)

Session recording and playback

Advanced whiteboard tools

Material library with search

In-app messaging

Advanced analytics

Progress tracking

# Budget Overview

## Development Costs (4 months)

| Category | Cost (USD) |
| --- | --- |
| Development Team |  |
| Design Services |  |
| Third-party Services |  |
| Testing & Tools |  |
| Contingency |  |
| TOTAL |  |

## Monthly Operating Costs (Post-Launch)

| Service | Monthly Cost (USD) |
| --- | --- |
| Hosting & Infrastructure | $50 - $200 |
| Database | $25 - $100 |
| Video Service (Agora) | $100 - $500 |
| Email & Other Services | $50 - $150 |
| Monitoring & Tools | $20 - $100 |
| TOTAL | $245 - $1,050 |

Note: Monthly costs scale with usage. Estimates are for 100-500 active users.

# Key Risks & Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Timeline delays | High | Weekly sprints, daily standups, buffer time |
| Video integration complexity | Medium | Use proven Agora SDK, early testing |
| Payment gateway issues | High | Start early, 2-week allocation, sandbox testing |
| Low user adoption | High | Marketing strategy, beta testing, referral program |
| Security vulnerabilities | High | Regular audits, security testing in Week 16 |

# Launch Strategy

## Week 1 (June 1-7): Soft Launch

Invite 20-30 beta users

Monitor system closely

Fix critical issues immediately

Collect feedback

## Week 2-3 (June 8-21): Limited Launch

Open with invite codes

Grow to 100-200 users

Continue improvements

Gather testimonials

## Week 4+ (June 22+): Public Launch

Open public registration

Marketing campaign

Press releases

Social media promotion

# Success Metrics

| Metric | Target | Measurement |
| --- | --- | --- |
| System Uptime | 99.9% | Continuous monitoring |
| Page Load Time | < 3 seconds | Lighthouse testing |
| API Response Time | < 500ms | Performance monitoring |
| User Registrations | 50+ in Month 1 | Analytics dashboard |
| Session Bookings | 100+ in Month 1 | Database tracking |
| Session Completion | > 95% | Platform metrics |
| User Satisfaction | > 4.5/5 | Post-session surveys |
| Payment Success | > 98% | Payment logs |

# Critical Path to Launch

These items MUST be completed on schedule to meet the June 1 launch date:

Week 2 - Feb 16: Authentication system operational

Week 4 - Mar 2: Tutor search and profiles working

Week 6 - Mar 16: Booking system functional

Week 11 - Apr 20: Virtual classroom complete

Week 13 - May 4: Payment integration done

Week 16 - May 25: All testing complete, bugs fixed

Week 17 - May 31: Production deployment successful

Any delay in these critical milestones will require immediate escalation and may impact the launch date. Weekly status reviews will track progress against this critical path.

# Week-by-Week Summary

| Weeks | Phase | Key Activities |
| --- | --- | --- |
| Weeks 1-2 | Setup & Foundation | Dev environment, database, authentication |
| Weeks 3-4 | Tutor Discovery | Search, filters, tutor profiles |
| Weeks 5-6 | Scheduling | Booking system, calendar, email notifications |
| Weeks 7-8 | Dashboards | Student/tutor dashboards, notifications, settings |
| Weeks 9-11 | Virtual Classroom | Video integration, whiteboard, chat |
| Weeks 12-13 | Payments | Payment gateway, DPU, escrow, payouts |
| Week 14 | Verification | Session tracking, completion system |
| Weeks 15-16 | Testing & QA | Comprehensive testing, bug fixes, optimization |
| Week 17 | Launch Prep | Deployment, documentation, soft launch |

--- End of Brief Timeline ---